## Tabelle1
issue | Description | Severity | Status | Update
#i01 | Error in design_elaborator.merge when running MIMO_Solver_N2 and _N4 | CRITICAL | SOLVED | SST dictonary registration added in ternary merge function (design_elaborator.py, line261) SST node replace has been adapted to ternary nodes, hanlding of 3rd sibling has been added (type_SST.py, line 170)
#i02 | RAM exeeded in robotic kinematics example | CRITICAL | SOLVED | deepcopy call changed to copy
#i03 | Input ports with the same label are generated in the toplevel VHDL file (Issue seems to also propogate to submodules in some examples) | CRITICAL | SOLVED | during architectural build, existing toplevel input ports are compared to ports of the acutal entity
#i04 | Pipelining does not work with fused operands (Deadlock) | CRITICAL | SOLVED | maxDepth parameter of SST has been changed to depth when accessed in the insertRegister function
#i05 | Several instances of the same arithmetic unit | LOW | REPORTED | Reproducable in kinematik.sorn
#i06 | Bad labeling of arithmetic units | LOW | REPORTED | MUL0ADD4 -> tMULADD_i1i1i1o1
#i07 | Test script is missing | MEDIUM | REPORTED | csh script that compares the outcome of modified/updated sorngen with existing golden references
#i08 | Register Insertion for full design (Toplevel-oriented) | CRITICAL | OPEN
#i09 |  | CRITICAL | OPEN
#i10 |  | CRITICAL | OPEN
#i11 |  | CRITICAL | OPEN
#i12 |  | CRITICAL | OPEN
#i13 |  | CRITICAL | OPEN
#i14 |  | CRITICAL | OPEN
#i15 |  | CRITICAL | OPEN
#i16 |  | CRITICAL | OPEN
#i17 |  | CRITICAL | OPEN
#i18 |  | CRITICAL | OPEN
#i19 |  | CRITICAL | OPEN
#i20 |  | CRITICAL | OPEN
#i21 |  | CRITICAL | OPEN
#i22 |  | CRITICAL | OPEN
#i23 |  | CRITICAL | OPEN
#i24 |  | CRITICAL | OPEN
#i25 |  | CRITICAL | OPEN
#i26 |  | CRITICAL | OPEN
#i27 |  | CRITICAL | OPEN
#i28 |  | CRITICAL | OPEN
#i29 |  | CRITICAL | OPEN
#i30 |  | CRITICAL | OPEN

## Tabelle2
NONE | REPORTED
LOW | OPEN
MEDIUM | IN PROGRESS
HIGH | SOLVED
CRITICAL | UNSOLVABLE